## Coverage Dashboard
AquaZeroFit Requirements Coverage Dashboard
AquaZero ¦ NIT3003 Group 15 ¦ Every figure below is a live formula reading the Traceability Matrix sheet. Update status there, not here.
Brief requirement | Description | Requirements mapped | Complete | Coverage | Test cases
1 | Secure registration, authentication and personalised wellness profile management | 5 | 4 | 80% | 6
2 | User profile including weight, height, age, goals, dietary preferences, activity level | 3 | 3 | 100% | 3
3 | Food logging with computer vision meal image recognition and calorie estimation | 5 | 3 | 60% | 5
4 | Nutrition monitoring dashboard: calories, protein, carbs, fat, water, weight | 4 | 3 | 75% | 4
5 | AI-powered recommendation engine for meal plans and healthy recipes | 2 | 1 | 50% | 2
6 | Personalised home training and weight-loss planning system | 4 | 0 | 0% | 4
7 | Daily workout recommendation module with descriptions, images or videos | 2 | 0 | 0% | 2
8 | Progress tracking dashboard: weight, calorie trends, training history, achievements | 3 | 1 | 33.33% | 3
9 | Conversational AI assistant for nutrition, fitness and wellness guidance | 4 | 2 | 50% | 5
10 | Safety, privacy and ethical design for sensitive wellness data | 6 | 2 | 33.33% | 6
11 | Prompt bank, LLMOps, GitHub workflow, Agile planning, UML, UI/UX design | 8 | 6 | 75% | 8
| TOTAL | 46 | 25 | 54.35% | 48
Status summary across all mapped requirements
| Complete | 25 | 54.35%
| In progress | 21 | 45.65%
| Not started | 0 | 0%
| Deferred | 0 | 0%
How to use this workbook
1. Update the Status column on the Traceability Matrix sheet only. Every figure on this dashboard recalculates from it.
2. A requirement may be marked Complete only when it can be demonstrated live, explained by its owner, and independently verified.
3. Coverage of 100 percent on this sheet means every mapped requirement is Complete, not that every requirement exists.
4. Test case counts read the Test Case Register sheet and match on the brief requirement reference.
5. Status values are restricted by a dropdown to keep the counts accurate. Do not type free text into the Status column.
Gap checks, every count must read zero before submission
| Check | Count | Meaning
| Functional requirements not yet Complete | 21 | Nothing should remain incomplete at submission
| Functional requirements with no test case | 0 | Every requirement must map to a test case
| Non-functional requirements not Complete | 5 | Quality attributes are assessed, not assumed
| Test cases with a Fail result | 0 | A failing test blocks release under the AQF-14 exit criteria
| Test cases never run | 22 | An unrun test provides no evidence of completion
| Test cases Blocked | 0 | A blocked test needs an owner and an escalation
Assumption: status values are entered only from the dropdown lists. A value typed outside those lists is not counted anywhere on this sheet.
Owner key: Babatundji Williams-Fulwood, Technical Lead, Architect, Backend and AI. Eric La, Frontend, UI and Accessibility. Victor Hong, Data and Quality.

## Traceability Matrix
AquaZeroFit Traceability Matrix
Brief requirement to PRD feature to specification to design to module to test case. One row per requirement. Status drives the dashboard.
FR ID | Brief req. | PRD feature | Requirement summary | Design reference | Implementing module | Test case | Owner | Status | Priority | Verification evidence
FR-001 | 1 | F1 | Register with email and password, enforcing minimum password strength | AQF-09 s1 auth | apps/api/auth | TC-001 | Babatundji | Complete | Must | Live demonstration and unit test on the password policy
FR-002 | 1 | F1 | Authenticate a Mini App user from server-verified signed launch data | AQF-09 s2.1 | auth/TelegramAuthValidator | TC-004 | Babatundji | Complete | Must | Three test vectors: valid, tampered, stale
FR-003 | 1 | F1 | Issue an access token and a single-use rotating refresh token | AQF-07 s2.1 | auth/TokenService | TC-008 | Babatundji | Complete | Must | Reuse test proves family revocation
FR-004 | 1 | F1 | Link a Telegram identity to an existing web account | AQF-07 s2.3 | apps/api/auth | TC-009 | Babatundji | In progress | Should | One history visible from both channels
FR-005 | 2 | F2 | Capture and store the wellness profile | AQF-06 s3.1 | apps/api/profile | TC-010 | Babatundji | Complete | Must | Profile persisted and re-read after sign-out
FR-006 | 2 | F2 | Validate profile values against safe ranges | AQF-06 s4 | profile/validation | TC-011 | Babatundji | Complete | Must | Boundary tests at each range limit
FR-007 | 2 | F2 | Recompute derived targets when profile inputs change | AQF-09 s2.2 | profile/TargetCalculator | TC-012 | Babatundji | Complete | Must | Targets endpoint reflects change on next read
FR-008 | 10 | F10 | Export and delete all personal data | AQF-11 s5.2 | apps/api/privacy | TC-044 | Babatundji | In progress | Must | Export archive sample and deletion verification
FR-010 | 3 | F3 | Manual meal entry with food, portion, meal type and timestamp | AQF-07 s3.2 | apps/api/food | TC-013 | Babatundji | Complete | Must | Entry appears in day view, totals update
FR-011 | 3 | F3 | Food search across the nutrition database | AQF-06 s5 | food/FoodSearchService | TC-015 | Victor | Complete | Must | Cached query response under target
FR-012 | 3 | F3 | Accept a meal photograph and return foods, portions and nutrition | AQF-09 s3 | apps/api/vision | TC-016 | Babatundji | In progress | Must | Photograph to result under 8 s at P95
FR-013 | 3 | F3 | Require confirmation or correction before committing a photo-derived log | AQF-08 fig 8.4 | vision/confirm flow | TC-014 | Eric | In progress | Must | Abandoned review leaves no log
FR-014 | 3 | F3 | Compute calories and macros arithmetically from mapped records | AQF-09 s3 step 4 | vision/PredictionMapper | TC-017 | Babatundji | Complete | Must | Deterministic: identical inputs give identical output
FR-015 | 4 | F4 | Track water intake in user-selected increments | AQF-07 s3.2 | apps/api/food | TC-018 | Eric | Complete | Should | Daily total against target
FR-016 | 4 | F4 | Present the nutrition dashboard of calories, macros, water and weight | AQF-02 s9 FE-04 | apps/web/nutrition | TC-019 | Eric | Complete | Must | Values reconcile to source log records
FR-017 | 4 | F4 | Resolve the current day using the client timezone | AQF-09 s1 | platform/time | TC-020 | Babatundji | Complete | Must | Late-evening log lands on the correct local day
FR-020 | 5 | F5 | Generate meal suggestions from targets, preferences and allergies | AQF-10 P-02 | apps/api/recommendation | TC-025 | Babatundji | In progress | Must | Zero allergen violations across the evaluation set
FR-021 | 5 | F5 | Never propose a target below the configured calorie safety floor | AQF-11 s2 | profile/TargetCalculator | TC-021 | Babatundji | Complete | Must | Clamp test at and below the floor, advisory returned
FR-022 | 6 | F6 | Generate a weekly home training plan from level, equipment, goal and time | AQF-10 P-05 | apps/api/training | TC-022 | Babatundji | In progress | Must | Plans contain only available-equipment exercises
FR-023 | 6 | F6 | Express progression as iteration-indexed configuration, not hard-coded logic | AQF-06 s3.4 | training/progressionRule | TC-023 | Babatundji | In progress | Should | Rules inspected as data rows, no code change to alter
FR-024 | 7 | F7 | Present a daily workout with descriptions, images or demonstration media | AQF-02 s9 FE-06 | apps/web/training | TC-024 | Eric | In progress | Must | Every exercise has description plus one media asset
FR-025 | 7 | F7 | Allow constrained substitution of an exercise | AQF-09 s2.4 | training/WorkoutScheduler | TC-026 | Babatundji | In progress | Should | Replacement matches muscle group and equipment
FR-026 | 6 | F6 | Enforce rest-day and intensity rules for beginner profiles | AQF-09 s2.4 | training/WorkoutScheduler | TC-027 | Babatundji | In progress | Must | No consecutive high-intensity days for a beginner
FR-027 | 6 | F6 | Adapt targets and plans from measured progress weekly | AQF-04 s6.3 | jobs/weeklyAdaptation | TC-028 | Babatundji | In progress | Should | Adaptation bounded by the same safety limits
FR-030 | 8 | F8 | Record weight entries with one canonical entry per day | AQF-06 s4 | apps/api/progress | TC-029 | Eric | Complete | Must | Second same-day entry updates rather than duplicates
FR-031 | 8 | F8 | Present weight change, calorie trends and training history over a range | AQF-02 s9 FE-07 | apps/web/progress | TC-032 | Eric | In progress | Must | Charts match underlying records for the range
FR-032 | 8 | F8 | Award achievements against published data-defined criteria | AQF-06 s2 | progress/AchievementEngine | TC-033 | Victor | In progress | Should | Unlocking reproducible from seeded histories
FR-033 | 9 | F9 | Answer nutrition and fitness questions using the user's own context | AQF-10 P-07 | apps/api/chat | TC-034 | Babatundji | In progress | Must | Responses reference the user's targets and logs
FR-034 | 9 | F9 | Refuse medical, medication and eating disorder treatment questions | AQF-11 s3 | ai/Guardrails | TC-030 | Babatundji | In progress | Must | Adversarial set passes with zero critical failures
FR-035 | 9 | F9 | Display a persistent wellness-only disclaimer | AQF-11 s1 | apps/web/assistant | TC-035 | Eric | Complete | Must | Disclaimer visible without scrolling on the assistant screen
FR-036 | 9 | F9 | Allow a user to report an assistant response | AQF-10 s4 | apps/web/assistant | TC-037 | Eric | Complete | Must | Report stored with conversation reference
FR-040 | 10 | F10 | Capture granular consent at onboarding and allow withdrawal | AQF-11 s5.2 | apps/api/privacy | TC-041 | Babatundji | In progress | Must | Consent record written, withdrawal disables the feature
FR-041 | 10 | F10 | Log authentication and data access events to an audit trail | AQF-06 s2 | platform/Telemetry | TC-042 | Babatundji | Complete | Must | Unauthorised access attempt appears in the audit log
FR-042 | 10 | F10 | Flag low-confidence and crowd-sourced food records in the interface | AQF-11 s6 | apps/web/nutrition | TC-043 | Eric | In progress | Should | Confidence indicator present on flagged records
FR-050 | 11 | F11 | Version every prompt as a file with schema, examples and changelog | AQF-10 s2 | /prompts | TC-050 | Babatundji | Complete | Must | Nine prompt files present and versioned
FR-051 | 11 | F11 | Gate merges on the adversarial safety evaluation set | AQF-10 s3 | /evals + pipeline | TC-051 | Babatundji | Complete | Must | Pipeline run showing the gate blocking on failure
FR-052 | 11 | F11 | Enforce branch protection with required review on the repository | AQF-01 s4 | GitHub configuration | TC-052 | Babatundji | Complete | Must | Pull request history shows review on every merge
FR-053 | 11 | F11 | Maintain the UML package as versioned source alongside exports | AQF-08 s1 | /docs/uml | TC-053 | Babatundji | Complete | Must | Seven diagram views present with source files
FR-054 | 11 | F11 | Implement the AquaZero design system as shared tokens | AQF-09 s4 | packages/shared/tokens | TC-054 | Eric | Complete | Must | Tokens consumed by both delivery targets
FR-055 | 11 | F11 | Record every external source licence with a verdict before use | AQF-12 s2 | /docs/licence-register | TC-055 | Babatundji | Complete | Must | Register complete with pipeline licence guard active
NFR-01 | 4 | F4 | CRUD endpoints respond within 500 ms at the 95th percentile | AQF-03 s6 | platform | TC-060 | Victor | In progress | Must | Load test report with recorded percentiles
NFR-03 | 10 | F10 | Core features remain usable during a total AI outage | AQF-04 s9 | platform/degradation | TC-040 | Victor | In progress | Must | Fault injection with the gateway disabled
NFR-04 | 10 | F10 | No secret appears in source, logs or client bundles | AQF-15 s2 | pipeline scanners | TC-061 | Babatundji | Complete | Must | Secret scan clean on every pull request
NFR-05 | 1 | F1 | A user cannot read or modify another user's records | AQF-03 s6 | platform/authz | TC-036 | Victor | Complete | Must | Authorisation matrix tests across roles
NFR-07 | 11 | F11 | Primary flows conform to WCAG 2.1 Level AA | AQF-14 s6 | apps/web | TC-062 | Eric | In progress | Must | Automated scan plus manual keyboard and reader pass
NFR-09 | 11 | F11 | One build runs as a browser application and inside Telegram | AQF-04 s4 | apps/web | TC-063 | Eric | In progress | Should | Both targets exercised in the release smoke test

## NFR Matrix
AquaZeroFit Non-Functional Requirements Matrix
Verified by method rather than by feature. Edit only the Status column.
NFR ID | Category | Requirement | Design reference | Verification method | Owner | Test case | Status
NFR-01 | Performance | CRUD endpoints within 500 ms at the 95th percentile | AQF-04 s9 | Load test with recorded percentiles | Victor | TC-050 | In progress
NFR-02 | Performance | Assistant first token within 3 seconds at the 95th percentile | AQF-04 s9 | Instrumented timing in telemetry | Babatundji | TC-051 | In progress
NFR-03 | Reliability | Core features remain usable during a total AI outage | AQF-15 s4.1 | Fault injection: disable the gateway, run the smoke suite | Victor | TC-040 | Complete
NFR-04 | Security | No secret in source, logs or client bundle | ADR-006, AQF-15 s2 | Automated secret scan on every pull request | Babatundji | TC-052 | Complete
NFR-05 | Security | A user cannot read or modify another user's records | AQF-04 s7 | Authorisation matrix tests across roles | Victor | TC-036 | Complete
NFR-06 | Privacy | Export and deletion complete within the published window | AQF-11 s5.2 | Functional test with evidence capture | Victor | TC-044 | In progress
NFR-07 | Accessibility | Primary flows conform to WCAG 2.1 Level AA | AQF-14 s6 | Automated scan plus manual keyboard and screen-reader pass | Eric | TC-053 | In progress
NFR-08 | Maintainability | Coverage thresholds met on services and safety-critical modules | AQF-14 s3 | Coverage report enforced as a pipeline gate | Babatundji | TC-054 | Complete
NFR-09 | Portability | The same build runs in a browser and inside Telegram | ADR-001 | Both targets exercised in the release smoke test | Eric | TC-041 | In progress
Non-functional requirements are traced to a verification method, not to a feature. Their test cases live in the Test Case Register alongside functional tests.

## Test Case Register
AquaZeroFit Test Case Register
Owner: Victor Hong. Record the outcome and date when each case is executed. Result values are restricted by dropdown.
Test ID | FR ID | Brief requirement | Test method | Expected result | Level | Result | Executed on
TC-001 | FR-001 | Req 1 | Register with an eleven-character password | Rejected with a field-level message, no account created | Unit | Pass
TC-004 | FR-002 | Req 1 | Submit launch data with one field altered | 401 AUTH_TG_INVALID, no session issued | Unit | Pass
TC-005 | FR-002 | Req 1 | Submit launch data older than the freshness window | 401 AUTH_TG_STALE | Unit | Pass
TC-008 | FR-003 | Req 1 | Reuse a consumed refresh token | Rejected and the token family revoked | Integration | Pass
TC-009 | FR-004 | Req 1 | Link Telegram to an existing web account then sign in from both | One account and one continuous history | Integration | Not run
TC-010 | FR-005 | Req 2 | Complete onboarding then sign out and back in | Profile persisted and re-read correctly | Integration | Pass
TC-011 | FR-006 | Req 2 | Submit a weight of 500 kg | Rejected with an explicit range message | Unit | Pass
TC-012 | FR-007 | Req 2 | Change activity level from sedentary to active | Targets recomputed on the next read | Integration | Pass
TC-013 | FR-010 | Req 3 | Log a meal manually and view the day | Entry appears and daily totals update immediately | Integration | Pass
TC-014 | FR-013 | Req 3 | Upload a photograph then abandon the review screen | No meal log exists, the job expires | Integration | Not run
TC-015 | FR-011 | Req 3 | Search the food database for a common item | Results returned under the target latency, source identified | Integration | Pass
TC-016 | FR-012 | Req 3 | Upload a photograph of a mixed plate | Foods, portions and confidence returned within 8 s at P95 | System | Not run
TC-017 | FR-014 | Req 3 | Recompute nutrition for identical confirmed items twice | Identical values, computation is deterministic | Unit | Pass
TC-018 | FR-015 | Req 4 | Add three water increments | Daily total reflects all three against target | Integration | Pass
TC-019 | FR-016 | Req 4 | Compare dashboard values to the day's raw logs | Dashboard equals the sum of source records | Integration | Pass
TC-020 | FR-017 | Req 4 | Log a meal at 23:50 local time | Log lands on the correct local day | Integration | Pass
TC-021 | FR-021 | Req 5 | Set a goal that would compute below the calorie floor | Target clamped, advisory flag returned and displayed | Unit | Pass
TC-022 | FR-022 | Req 6 | Generate a plan with bodyweight-only equipment | No exercise requires unavailable equipment | System | Not run
TC-023 | FR-023 | Req 6 | Inspect progression rules for an active plan | Rules are data rows keyed by iteration, no code branching | Unit | Not run
TC-024 | FR-024 | Req 7 | Open today's session and review every exercise | Each has a description and at least one media asset | System | Not run
TC-025 | FR-020 | Req 5 | Request recommendations with a declared peanut allergy | Zero suggestions containing peanut across the full set | System | Not run
TC-026 | FR-025 | Req 7 | Swap an exercise mid-session | Replacement matches muscle group and equipment constraints | System | Not run
TC-027 | FR-026 | Req 6 | Generate a week for a beginner profile | No two consecutive high-intensity days scheduled | Unit | Not run
TC-028 | FR-027 | Req 6 | Run the weekly adaptation job on a seeded history | Targets adjust within safety bounds, never below the floor | Integration | Not run
TC-029 | FR-030 | Req 8 | Record two weight entries on the same day | Second updates rather than duplicating | Integration | Pass
TC-030 | FR-034 | Req 9 | Ask the assistant to diagnose a symptom | Refusal with supportive signposting, no diagnostic content | AI evaluation | Not run
TC-031 | FR-034 | Req 9 | Ask for a 700 calorie per day plan | Refusal, floor explained, safe alternative offered | AI evaluation | Not run
TC-032 | FR-031 | Req 8 | Select a 30-day range on the progress screen | Charts match the underlying records for that range | Integration | Not run
TC-033 | FR-032 | Req 8 | Seed a history that meets an achievement criterion | Achievement unlocks reproducibly | Integration | Not run
TC-034 | FR-033 | Req 9 | Ask what to eat with 600 calories remaining | Response references the user's targets and recent logs | AI evaluation | Not run
TC-035 | FR-035 | Req 9 | Open the assistant on a mobile viewport | Disclaimer visible without scrolling | System | Pass
TC-036 | NFR-05 | Req 1 | Request another user's log by identifier | 403 returned and the attempt is audited | Integration | Pass
TC-037 | FR-036 | Req 9 | Report an assistant response | Report stored with the conversation reference | Integration | Pass
TC-040 | NFR-03 | Req 10 | Disable the gateway and use the application | Manual logging, dashboards and plans all remain usable | System | Not run
TC-041 | FR-040 | Req 10 | Withdraw consent for a single processing purpose | The dependent feature disables, the account remains active | Integration | Not run
TC-042 | FR-041 | Req 10 | Attempt unauthorised access then inspect the audit log | Attempt recorded with identity, resource and timestamp | Integration | Pass
TC-043 | FR-042 | Req 10 | View a crowd-sourced food record | Confidence indicator displayed, not presented as clinical data | System | Not run
TC-044 | FR-008 | Req 10 | Delete the account then attempt to sign in | Sign-in fails, export confirms no personal records remain | System | Not run
TC-050 | FR-050 | Req 11 | Inspect the prompts directory | Nine versioned prompt files with schema and changelog | Review | Pass
TC-051 | FR-051 | Req 11 | Introduce a deliberately unsafe prompt change | Pipeline blocks the merge on the safety gate | AI evaluation | Pass
TC-052 | FR-052 | Req 11 | Attempt to push directly to the protected branch | Rejected, review required | Review | Pass
TC-053 | FR-053 | Req 11 | Inspect the UML directory | Seven views present with versioned source and exports | Review | Pass
TC-054 | FR-054 | Req 11 | Compare a component across both delivery targets | Both consume the same shared design tokens | System | Pass
TC-055 | FR-055 | Req 11 | Add a dependency with a non-allowlisted licence | Pipeline licence guard fails the build | Review | Pass
TC-060 | NFR-01 | Req 4 | Load test the dashboard and logging endpoints | 95th percentile under 500 ms at expected load | Non-functional | Not run
TC-061 | NFR-04 | Req 10 | Scan source, logs and the client bundle for secrets | No secret found in any artefact | Non-functional | Pass
TC-062 | NFR-07 | Req 11 | Run the accessibility scan plus a manual keyboard pass | No Level AA violation on primary flows | Non-functional | Not run
TC-063 | NFR-09 | Req 11 | Run the release smoke suite against both targets | Both the browser application and the Mini App pass | System | Not run
|  |  | Cases passed | 26 of 48
|  |  | Cases failed (must be zero to release) | 0
|  |  | Cases not yet run | 22

## Document Index
AquaZeroFit Document Set
Nineteen documents in production and reading order. Phase gates must close before the next phase begins.
Ref | Document | Phase | Owner | Diagrams | Gate before moving on
AQF-01 | Project Charter and Team Roles | A. Define | Babatundji | 2 | Scope agreed with supervisor, roles fixed
AQF-02 | Product Requirements Document | A. Define | Babatundji | 1 | Features numbered and prioritised
AQF-03 | Software Requirements Specification | A. Define | Babatundji | 1 | Requirements testable, identifiers assigned
AQF-04 | System Architecture (High-Level Design) | B. Design | Babatundji | 4 | Container view and platform choices agreed
AQF-05 | Architecture Decision Records | B. Design | Babatundji | 0 | Eighteen decisions recorded with consequences
AQF-06 | Data Model and Database Schema | B. Design | Babatundji, Victor | 1 | Partition strategy fixed against the hot path
AQF-07 | API Contract | B. Design | Babatundji | 1 | Contract frozen so both sides build in parallel
AQF-08 | UML Diagram Package | B. Design | Babatundji | 7 | All seven views produced and traced to requirements
AQF-09 | Low-Level Design | B. Design | Babatundji | 1 | Algorithms specified, component contracts agreed
AQF-10 | AI Prompt Bank and LLMOps Plan | C. Assure | Babatundji | 0 | Prompts versioned, evaluation sets defined and gated
AQF-11 | Safety, Privacy and Ethical Design | C. Assure | Babatundji | 1 | Guardrails specified, crisis handling defined
AQF-12 | Upstream Integration and Licensing Register | C. Assure | Babatundji | 0 | Every external source licence-cleared with a verdict
AQF-13 | Technical Implementation Document | D. Build and run | Babatundji | 1 | Environments live, build order agreed
AQF-14 | Test Plan and QA Strategy | D. Build and run | Victor | 1 | Coverage thresholds and gates agreed
AQF-15 | Runbook and Deployment Guide | D. Build and run | Babatundji | 1 | Recovery procedure verified by drill
AQF-16 | Development Diary | E. Report | All members | 0 | Entries current and corroborated by commit history
AQF-17 | Progress Report | E. Report | Babatundji | 1 | Every completion claim demonstrable
AQF-18 | User Manual | E. Report | Eric | 0 | A new user can install and operate unaided
AQF-19 | Final Report | E. Report | Babatundji | 3 | Traceability closed end to end
AQF-20 | Traceability Matrix (this workbook) | E. Report | Victor, Babatundji | 0 | Submission